## Final
Date : Nov 29, 2015	11/26/15	Team :	JCREL
Task	Status	Notes	Assigned to	Priority
Include “Quick Add” link for the suppliers and locations in Arrival Page	Completed		Catherine
Implement exceptions in Sales Page – Item quantity should be changed when adding sales	Completed		Erikka
Fix the formsets in the Sale, Transfer and Arrival page	Completed		Roselle
Sale Page: Remove item_cost in Sale Page, and include item location in Item model	Completed		Erikka
Merge and fix conflicts – JCREL branch into Dev branch – Dev branch into Master Branch	Completed		Erikka
Filter feature in Arrival, Sales and Transfer History	Completed		Roselle
Extend Django's User model into our own Account model – in order to include avatar and other user details	On-going	80% Complete – Update the update settings page to include all user and accounts fields	Josiah
Implement ItemLocation model – the intermediary between Item and Location.	On-going		Loreinne
Ability to choose the item once in the formsets	Todo
Reports Feature	Todo		Roselle
Improve design in formsets	Todo		Josiah
Add minimum_quantity_required in item model	Todo		Josiah
Update notification feature – use the minimum quantity required to check if the stock level is below minimum	Todo		Josiah

Date : December 3 2015	Team : JCREL
Task	Status	Notes	Assigned to	Priority
Improve formset designs and history pages		Create logo	Everyone
Add minimum_quantity_required in item model, Update notification feature – use the minimum quantity required to check if the stock level is below minimum			Josiah
Implement success messages after adding item, or deleting item, or updating			Erikka
Extend Django's User model into our own Account model – in order to include avatar and other user details	Almost Completed	Already done, but needs to add more fields like address	Josiah
Implement ItemLocation model – the intermediary between Item and Location.			Loreinne
Improve filter feature in history pages	Use ajax, add filter feature in sales and transfer		Roselle
Success Message on login, logout, submit form			Erikka
Dynamic Report Charts			Roselle

Date : December 7 2015	Team : JCREL
Task	Status	Notes	Assigned to	Priority
Review database design, and update models	On-going	See Sheet 2 (GO TEAM!)	Everyone	High
Create tests for each model	On-going		Everyone	High
Think of the different functions for your models - Implement these model functions (Best practice: Fat models, stupid views)	On-going	See Sheet 2 (GO TEAM!)	Everyone	High
Create tests for each function in model	On-going		Everyone	High
Create script for initializing data	On-going		Roselle	Medium
Export to PDF / CSV – Reports & Data	On-going		Roselle	Low
Create and update existing forms for each model	On-going		Everyone	Medium
Create formsets for manytomany models	On-going		Everyone	Medium
Lead planning of page designs	On-going		Catherine	Medium
Lead updates of sequence diagrams	On-going		Erikka	Medium
Update notification models – add functionality for creating notifications	On-going		Josiah	Medium
Landing page design – team & contact us section	On-going		Erikka	Medium
Landing page design – create “about product / product features” section	On-going		Loreinne	Medium
Arrival page design and update of functionalities	Completed		Catherine	High
Login page design & template	On-going		Catherine	Medium
Landing page design – banner section	Completed		Catherine	Medium

Date : December 10 2015	Team : JCREL
Task	Status	Notes	Assigned to	Priority
Implement update of item quantities during arrivals (If wala pa)	On-going		Catherine
Landing page update - Add menu links in landing page based on sections (Home, About Us, Features, Contact, etc.) - Add content for each sections			Erikka
Implement update of item quantities during sales (If wala pa)			Erikka
Update docs		Deadline: Mon?	Everyone
Remove user profile link in navbar right dropdown			Josiah
Merge update account settings into one page or update base template for change password			Josiah
Notifications dropdown: Implement conditional – No messages should be put if there are no notifications. Currently, it's just blank - try placing a message like "No notifications churva"			Josiah
Update logout page template			Loreinne
Update login and signup page template		Currently, dli mkabalik ang user sa home page, so dapat naa japon ang menu dri na mga pages. hihi	Loreinne
Update dashboard primary page template			Roselle
Update sales, arrival and transfer history			Roselle
Restore and fix inventory and sales reports			Roselle
Host app in openshift			Roselle
Make the navbar on the left FIXED		kinsa gusto mag kubi2 ani?
Delete django-notifications and toast files in repostory if not used - Also clean javascript and css files not used			Josiah
Error in adding transfer - review?			Loreinne
Optional: Add pages for each item
Updating quantity of an item in specific location when transfer occurs			Loreinne
Implement pagination in history and pages (If not yet)
When choosing an arrival item, make sure that the item gets chosen once only.			Catherine
Errors in transfer item	On-going		Loreinne
Update Add Item - Set item quantities per location zero by default			Roselle
Limit the landing page items quanitty

## GO TEAM!
Database Design

Roselle	Erikka	Erikka	Roselle	Roselle	Loreinne	Loreinne	Catherine	Catherine	Loreinne	Loreinne	Josiah	Josiah
Item	Sale	ItemSale	Customer	Supplier	Location	ItemLocation	Arrival	ItemArrival	Transfer	ItemTransfer	Notification	Account
is_active	transaction_date	quantity	name	name	name	item	date	quantity	source_location	quantity	date	avatar
category	location	item	address	address	address	location	dr_no	supplier_cost	destination_location	transfer	message	user
brand	customer	sale	phone	phone	user	re_order_point	tr_no	item	date	item	user	address (city, province, zip code, country)
model	user		photo	photo		re_order_amount	supplier	arrival	user			phone
name			user	user		current_stock	location
description					user
item_code
unit_cost
date_created
location
supplier
user

Model Functions

## Sheet4
todo
Make navbar on the left side fixed